## Slide 1: Provider Collaborative Workstream – Friday, 18th February 2022
Diane Wake, Chief Executive and SRO Provider Collaboration BCWB
Jonathan Odum, Medical Director Lead for Provider Collaboration BCWB

## Slide 2: Black Country Provider Collaborative
Overview of Progress to date

## Slide 3: Programme Governance from Dec 2020- April 2022
Initial development of improvement programme and timeline

## Slide 4: Acute Care Collaboration Governance at Dec 2020
SWBH Board
DGFT
Board
RWT
Board
WHT
Board
Acute Care Collaboration
Programme Board
Clinical improvement Programme
Shared efficiency & infrastructure programme
(Lead James Green)
Communication & Engagement
(Lead: Sally Evans)
STP/
ICS
Reset/
ICP (System-wide)
Governance & Implementation
Delivery
Lead: Directors of strategy DGFT; Exec Leads & Programme Team
Clinical Transformation
Lead: Jonathan Odum; Diane Wake Clinical Leaders
Inform & Influence
Lead link: Tom Jackson
Overall oversight
Lead: Diane Wake
Clinical Leadership Group
(System-wide)
DoFs Meeting
(System-Wide)
STP Governance
Sovereign Boards (existing)
ACC (new)
Intelligence, Insight & Outcomes
Evidence & Benefits realisation monitoring
Lead: Glenda Augustine; BI leads/Academy
Clinical Learning Networks
Boards: Each Board remains as a sovereign accountable entity with existing accountability and responsibilities unless delegated to Committees in Common (CIC); Governors remain for FT
People Board (System-wide)
Clinical Reference Group
Inform & Influence
Lead link: Alan Duffell
Leadership, Workforce & OD Programme
(Lead Alan Duffell)

## Slide 5
Clinical improvement Programme (Transformation oversight; engage and empower clinicians)
Drive clinically driven ambitious vision for collaboration which improves patient outcomes & experience, implementing evidence based pathways which reduces unwarranted variation, develop services and utilise peer review to implement evidence based pathways and drive forward quality improvement through clinical engagement & shared clinical leadership.
Clinical priorities tbc:
1. Agree scope; essential place services aligned to ICPs; and sustainably vulnerable services (i.e. workforce or scale/demand) to develop centres of excellence and agree/implement plans and develop joint STP/ICS Clinical Strategy
2. Improve cancer pathways and outcomes (align to Cancer Board)
3. Clinical leadership; infrastructure and dedicated resources to support delivery i.e. Appropriate delivery workstreams & projects, Clinical Leadership, PMO, digital, estate, workforce, data, diagnostics etc
Leadership/Workforce Programme (overseen by People Board – Alan Duffell)
Compelling shared vision for the collaboration and consistent simple messaging for staff and stakeholder. Provide an inspiring collaboration for our current and future workforce; Invest in leadership relationships and culture; Shared value and behaviours; Support Clinical Improvement priorities with data & resources as required to improve sustainability; Leadership development – once established consideration of any dedicated Acute Care Collaboration work required
Shared efficiency & infrastructure programme (overseen by System DoFs – James Green)
Improve system working to enable clinical improvement and sustainability. Identify and jointly agree and implement priorities with biggest impact. Consider shared teams and resources to deliver STP/ICS priorities whilst maintaining BAU. Consider shared financial controls and opportunities. Oversight through DoFs and delivery through DDoFs and additional functions as required. Scope opportunities and benefits and put plans in place to deliver. Priorities for Acute Care Collaboration to resource programme, particularly PMO and analytical/BI resource. Utilise and link to existing digital, estates etc work programmes. Develop system-wide CIPs.
Communication & Engagement
Engage with all stakeholders on change; keep all stakeholders informed. On-going comms and engagement plan to be developed and implemented.
Governance & Implementation Sub-group (Delivery)
Ensure all work programmes are well governed, planned, resourced and on-track and that all interdependencies are appropriately managed; communication and engagement is appropriate and that all risks are captured and mitigated. Ensure programme Director and PMO are held to account; Weekly meeting to include Programme Director and Executive Leads (Katherine Sheerin, Glenda Augustine, Simon Evans, and Dave Baker; PMO to be invited as established and required
Diane Wake (DGFT)
Programme Board (Oversight & Accountability)
Oversee delivery, assurance to sovereign Boards and STP/ICS Board; Hold programme leads to account; Challenge and drive ambition; Agree scope, priorities, plan and resources; Manage and mitigate overall risk; Align to and influence system priorities; Monthly meeting until established (review at 6 months)
Simon Evans
(RWT)
System-wide aligned to ACC priorities
Alan Duffell (RWT)
Tom Jackson (DGFT)
Jonathan Odum (RWT) and Diane Wake (DGFT)
Glenda Augustine (WHT)
Intelligence, Insight and Outcomes Programme (Support Clinical Transformation)
Ensure systematic peer review process using data to improve through clinically engaged, evidence based programme to remove unwarranted variation in access, outcomes and experience and link to system partners e.g. public health/ICPs/Mental Health (demand & capacity review; waiting lists; performance variances; model hospital; GIRFT; Mutual aid; COVID recovery; CQC; Quality Improvement methodologies to empower clinicians etc); monitor benefit realisation; support continuous evidence based improvement
Clinically driven Acute Care Collaboration (ACC)
Better care, experience and outcomes providing World Class Care in BCWB

## Slide 6
DATA & SOLUTIONS
SEP-FEB
2020/1
OCT-DEC
19
PROGRAMME BOARD
APPROVAL
ENGAGE WITH CEOS/CHAIRS & BOARDS
Case for Change
Engage with CEOs & Chairs to understand and agree approach
Approve Clinically driven approach with Boards
Identify leads
APR-SEP 19
JAN-MAR
2022
ACUTE CARE COLLABORATION -TIMELINE
APRIL
20
Agree Vision & governance
Agree approach to Intelligence, Insight & Outcomes
Agree approach to Clinical Engagement
Recommend approval to Boards
Outputs from approach to intelligence e.g. self-assessments/supply
Gap analysis to inform
Engage & develop solutions and measures
Adapt plans to reflect
Approval of plans
External review ‘art of the possible’
PHASE 1
PHASE 2
Business cases
Staff consultation
Internal planning and project management
Implement
Monitor benefit realisation
Review phase 1 for lessons learnt
Approve and implement phase 2 taking into account learning
DEC- MAR 2022/23
SEP-DEC 2020
MAR
2021
APR
2021
MAY-JUN
2021
JUL-DEC
2021
BOARD APPROVAL & IMPLEMENT
Approve plans and governance
Support as priority and commit resources
Detailed planning with leads
Commit resources
Agree Vision & next steps
LAUNCH & ANALYSE
Detailed planning with leads
Launch Event
Analyse intelligence, outcomes and finance Develop systematic approach to data to inform plans, and continuous improvement
COMMUNICATION
INTELLIGENCE, ENGAGE & PLAN
IMPLEMENTATION
DETAILED PLANNING & LAUNCH
SCOPE, GOVERNANCE & VISION
ENGAGE & INFORM
Develop clinical case for change
Engage with external partners and patient groups
CONSULT & COMMENCE
Commence implementation on low impact areas
Wider consultation on any high impact changes
MAR- JUL
2022
AUG-NOV
2022

## Slide 7
Draft Programme plan and timing
Phase 1. Case for Change & Set up
Phase 2. Launch, Detailed design and Implementation
Ph 3. Transformation and Optimisation
Shared Clinical improvement programme
Vision, Governance, Leadership and Culture
Shared Efficiency & Infrastructure programme
Delivery:
Form follows function
Vision. Share ambition with stakeholders and agree engagement
Governance. Approve high level plan and governance at Programme Board, for approval at sovereign Boards; align governance to STP and reset & recovery
Leadership & Relationships. Engagement and agreement of vision with senior leaders, and influence STP
Appointments. Agree SROs and Programme Board membership
Plan. Draft case for change; high level plan and governance for programme; and identify resource requirements
Independent support. Engage experts to support development of plans and capture of analytical evidence to support in readiness for engagement when capacity allows
Governance. Align governance and plans with STP, ICP and restoration & recovery
Design principles. Engage with system to develop approach to shared systemwide improvement, with reporting line to Programme Board
Intelligence approach & Sustainability review: Share scope and propose plan to inform detailed planning and prioritisation
Shared information. Propose approach to support systematic sharing of data for improvement through Intelligence, Insight and Outcomes programme
Agree process to update Boards
Agree high level plan and resources at March Programme Board
Shared ownership – SROs and membership identified from across organisations and functions
Phasing and operating mechanisms – identify and agree best model to deliver against plans, priorities and manage interdependencies e.g. reset & recovery; place; workforce etc
Vision. Develop compelling vision and engage widely
Leadership & Relationships Continued engagement in STP programme; build relationships at all levels and elements reporting to Programme Board
Shared leadership. Review & assess benefits of shared leadership
Comms. Agree and implement comms & engagement plan.
Board development. Space for boards to openly discuss patient and staff benefits of closer working; review governance including delegated powers
Prioritise. Clinical engagement to agree clinical priorities e.g. Cancer, centres of excellence
Empower & resource. Share vision, agree priorities, plans and resources with clinicians; set up/amend any working groups required to deliver
Clinical models. Clinical engagement to develop detailed plans for solutions, benefits and required investments.
Detailed service design, business cases and transition – Wave 1 services
Design and mobilisation. Prioritise, plan and resource with system; fully engage and align to existing system programmes eg Digital to support clinical improvement; shared IT; shared estates
Resource. Virtual teams and resources in place to support overall collaboration programme
Business cases for shared services models, and address sustainability risks
Shared services implemented eg. shared bank, business intelligence
Shared financial governance/control totals. Assess benefits
Review: Assess delivery mechanism and whether alternative approach could improve the benefits or pace of delivery based on evidence from engagement
MOU for collaborative working
Delivery of revised workforce sharing, recruitment and retention models
Enable: Strategies to enable cross-organisation working
Commissioning and contracting. Influence shadow approach and assess opportunities from collaboration
Ambition. Engage on vision and plans of services
Leadership & Relationships. Continued engagement in STP programme; development activities and potential shared leadership options
Embed culture of group working (if agreed)
Comms. Public comms and staff comms around new ways of working and benefits.
Review sustainability impact of work to date
Develop models and business case for Wave 2 services with clinical leaders
Identify opportunities to improve speed to benefit realisation
Identify further areas for collaboration
Review sustainability impact of work to date
Develop models and business case for Wave 2 services prioritised with clinical leaders
Improve pace to benefit realisation. Identify, learn and update plans
Identify further areas for collaboration
Corporate acts as the shared “brain” of the group (if agreed) or integrated teams
Review effectiveness of arrangements to date
Consider legal arrangements - contractual joint venture / partnership (if applicable)
Commissioning and contracting. Agree ways to organise relationships with commissioners for April 2022 contracting.
Dec 20 – Jul 21 (M1 -8 )
Aug 21 – Mar 22 (M9 – 18)
Apr 22– Feb 23 (M19 – 30)
Phase implementation over 30 months

## Slide 8: Board & Programme Governance from April 2022
Factoring in additional roles and responsibilities

## Slide 9: DRAFT Board Structure from 2022:
Black Country Provider Collaborative Board
Chair:
Membership: RWT, SWBH, WHT, DGOH,
Associate Membership: TBC
Acute Provider Improvement Portfolio
SRO: Diane Wake
Membership
Urgent Care Committee
SRO Richard Beeken:
Membership
Elective and Diagnostic Committee
SRO: Diane Wake
Membership:
Cancer Committee
SRO: Diane Wake
Membership:
Clinical Improvement Programme
Lead: Jonathan Odum/ Diane Wake
Corporate Improvement Programme
Lead: Tom Jackson
Governance and Implementation
Lead: Simon Evans
Comms and Engagement
Lead: Sally Evans
Intelligence and Insight
Lead: Glenda Augustine
Elective Ops Group
Lead: Liam Kennedy
Diagnostic Ops Group
Lead: Danielle Joseph
Cancer Operational Group
Lead: Gwen Nuttall
Diagnostic Improvement Programme
Lead: Danielle Joseph
HR, OD and Workforce
Lead: Alan Duffell
Digital, Data and Technology
Lead: Adam Thomas
Clinical Networks:
-ENT, Gynae, Opthal; Ortho, Colorectal, breast, urology, Critical Care, Skin.
Corporate Efficiency: Payroll, procurement, legal, finance, governance, HR and IT
Black Country Provider Collaborative Executive
Chair:
Membership: RWT, SWBH, WHT, DGOH
Delivery of Integrated Projects
Delivery of operational standards as a system
Delivery of shared vision, based on evidence and good engagement.
Notes: Underneath the Black Country Provider Collaborative Board –we need an Executive Group
The Executive Group would meet monthly and the Board either BI monthly or quarterly

## Slide 10: Programme Governance
Black Country Provider Collaborative Board
Exec Programme Board
Clinical Improvement Steering group
Back Office Improvement Steering group
Clinical Networks
Delivery Workstreams

## Slide 11: Clinical Reconfiguration/Improvement Programme
Development of Programme and key areas of prioritisation

## Slide 12: Target Operating Model
Future State
Specialist clinical services provided via hub and spoke models
Established culture of working together
Mature environment of knowledge sharing across teams at all levels.
Current State
Four Acute NHS trusts
Most clinical services provided across all four organisations
Emerging culture of working together
Limited sharing of knowledge and learning across teams at all levels

## Slide 13: Clinical Engagement
Three clinical summits held from June – Sept 2021
Fourth planned for March 22
Focus on developing the clinical vision in key areas and getting teams to understand how they could work together to improve health outcomes
Very well received with 150+ attendees per summit
Recruitment for system clinical leads commenced Sept 21- all in place by Nov 21 (ENT, Ortho, ophthal, Urology, gynae, critical care, colorectal, breast and skin).
GP engagement event Jan 22– meet and greet with the clinical leads

## Slide 14: Clinical Network Structure
All have a Terms of Reference and core membership
Agenda covers the following:
  Clinical transformation plans
  Operational Performance- RTT and/or Cancer
  GIRFT action plans
  Implementation of recommendations from EY and/or cancer pathway reviews
  Mutual Aid
Networks are clinically led, with a clinical and operational lead for each and project management support.
Clinical Services Reconfiguration Steering Group
BC Urology Network
BC Critical Care Network
BC Breast Surgery Network
BC Gynaecology Network
BC Ophthalmology Network
BC Orthopaedic Network
BC Skin Network
BC ENT Network
BC Colorectal Network

## Slide 15: Critical Care Network Work Streams
ACCP development Programme
Lead: TBC
Expansion of training programme for Adult Critical Care Practitioners across the Black Country
Provision of enhanced care facilities outside of CCU (L1 and RSU)
Lead: TBC
Review of existing facilities and modelling of future requirements into plans
Data/Capacity Modelling system
Lead: TBC
Development of a CCU data system for the Black Country which gives real time capacity information and enables future service modelling
Policies and Procedures- sharing and standardization
Lead: TBC
Development of agreed model for enhanced care facilities through close working with Medical and Surgical teams.
Review of policies and procedures across all 4 trusts with expiration dates to start streamlining processes

## Slide 16: Orthopaedics
Data and Planning
Lead:
GIRFT recommendations
Lead:
Green / Cold site Surgical Model
Black Country Hand Trauma Service
Lead:
Lead:
Activity modelling, performance dashboards for network group, review of local audit data on clinical outcomes
Right procedure right place- review of work that can be moved out of theatre environment
HVLC- review standard numbers per list for key procedures
Link with surgical hubs proposal- Cannock and Sandwell expansions
Complex work sent to QEH, but 5-6 straight forward cases per day (across 4 trusts) could be managed centrally.

## Slide 17: Skin
Primary Care referral & Teledermatology
Lead:
Clinic redesign
Lead:
Tertiary Services
Skin Cancer Hub and Spoke Model
Lead:
Lead:
oversees the creation of the one-stop clinic model, integrated multi-Speciality super-clinics and the creation of the Black Country Skin Hospital rapid access skin cancer hub
oversee the expansion of tertiary skin cancer surgery and oncology within the ICO and expansion of the ssMDT
Rapid access skin cancer model at the Hub
Staff at base and 1 day pw at hub
oversees the implementation of Teledermatology in secondary care, managing primary care referrals and triaging of referrals
Skin Cancer Pathology
Surgical Triage and Booking
Skin Cancer CNS, ACPs and Patient Pathway Support
Lead:
oversee the links between skin cancer services and the BCPS
Lead:
oversee the surgical triage process, surgical bookings and surgical pathways
Lead:
oversee the entire patient pathway ensuring seamless CNS support across the trusts. It will also review the development and expansion of CNSs, ACPs and Nurse Surgeons

## Slide 18: Breast
D&C modelling
Lead:
Oncoplastic/Reconstructive Unit
Lead:
Breast Imaging
Workforce Development
Lead:
Lead:
Pathway Standardisation
Lead:
Partnerships to reduce clinical cancellation at short notice, Dudley nurse led clinics, new consultant appointments at new cross and dudley
Utilise system D&C capacity (elective recovery fund)
Recruit TIG fellow from QE- support development of unit at RHH
Could SWBH provide breast imaging across BC? Improve demand by direct access to breast screening mammos by GPs/ protocolised access to community screening
ANPs, physician assistants, nurse led clinics, GPSIs
Referral form standardization, clinical triage, day case surgical rates, under 40s clinics on each site

## Slide 19: Back Office Improvement Programme

## Slide 20: Target Operating Model
Future State
Established culture of working together
Shared IT and informatics infrastructure and systems
Shared HR policies and processes
Mature environment of knowledge sharing across teams at all levels.
Current State
Four Acute NHS trusts
Emerging culture of working together
Separate IT and informatics infrastructure
Separate HR policies & processes
Limited sharing of knowledge and learning across teams at all levels